## Sheet1
Task |  | Person Responsible | Deadline |  | Task Status (+-) | Completion Date | Person Signing Off
1) Display product in frontent / Ebay UI/UX design from Google-Drive |  | Blocktec (Abdullah Khan) | 2022-09-15 |  | X
2) Add data products to frontent |  | Blocktec (Abdullah Khan) | 2022-09-15 |  | X
3) Product buy fuction implementation |  | Blocktec (Abdullah Khan) | 2022-09-15 |  | X
4) Test product in truffle |  | Blocktec (Abdullah Khan) | 2022-09-15
5) Build product details web page |  | Blocktec (Abdullah Khan) | 2022-09-15 |  | X
6) Buy from the web page |  | Blocktec (Abdullah Khan) | 2022-09-15 |  | X
7) Render Product Image Stored in IPFS encrypted |  | Blocktec (Abdullah Khan) | 2022-09-15
8) Add Image to IPFS from we frontend |  | Blocktec (Abdullah Khan) | 2022-09-15
9) Add description to IPFS from web frontend |  | Blocktec (Abdullah Khan) | 2022-09-15
10) Triple Check Escrow Implementation |  | Blocktec (Abdullah Khan) | 2022-09-15
11) Integrate Escrow into ECommerce Store. |  | Blocktec (Abdullah Khan) | 2022-09-15
12) Test Escrow Functionality |  | Blocktec (Abdullah Khan) | 2022-09-15
13) Integrate Escrow and Swap Contract |  | Blocktec (Abdullah Khan) | 2022-09-15 |  | Cross-check
14) Escrow Front End Implementation |  | Blocktec (Abdullah Khan) | 2022-09-15
15) Swap Front End Implementation |  | I8I | 2022-09-15
16) MongoDB Setup |  | I8I | 2022-09-15 | X
17) NodeJS Server SEtup |  | I8I | 2022-09-15 | X
18) Check Solidity Events |  | I8I | 2022-09-15 | X
19) Listen to Events |  | I8I | 2022-09-15
20) Save Events to MongoDB |  | I8I | 2022-09-15
21) Inspect MongoDB |  | I8I | 2022-09-15
22) Implement Search Medical Images API |  | I8I/Blocktec | 2022-09-15
23) Render Product on Front End |  | Blocktec (Abdullah Khan) | 2022-09-15 |  | X
24) Make sure that when an event fires when a product is purchases and updates the database with buy info. |  | Blocktec (Abdullah Khan) | 2022-09-15
25) Implement the filtering functionality in the frontend so you can categorize medical iamges. |  | Blocktec (Abdullah Khan) | 2022-09-15 |  | X
26) Implement a 2.5% fee for each transaction. |  | I8I/Blocktec | 2022-09-15
27) Create Arbiter Mode for Clinical Review of Data Authenticity or Dispute. Arbiter's must deposit $5 Ether to become an Arbiter. They can at any point change thier mind and get back their deposit. And when they do, they can no longer participate as an Arbiter. |  | I8I | 2022-09-15 | X | Cross-check
| - An Arbiter's deposite must be burned is they are discovered to be a bad actor, or has colluded with the buyer or the seller. | I8I/Blocktec | 2022-09-15
28) 5 Percent of profits are diverted to one wallet for Quantum Coin FOundation operating/programmatic |  | I8I | 2022-09-15
29) 5 Percent of profits go to Distributors/Arbiters(2.5%/2.5%) |  | I8I | 2022-09-15
30) 5 Percent of profits are for Data Miner Rewards to I8I |  | I8I | 2022-09-15
31) 5 Percent of profits are for for AI Workers to I8I |  | I8I | 2022-09-15
32) 5 percent of profits are for I8I Customer Ecosystem Rewards (Coin Drops/Incentives) |  | I8I | 2022-09-15
33) 30 Percent of profits go to the treasury for Claims, Liquidity, and Operations. |  | I8I | 2022-09-15
34) 80 percent of the profits going to the treasury for Claims, Liquidity, and Operations, will go into cold-storage in a lock-box at an FDIC protected banking institution. |  | I8I | 2022-09-15
34) 40 Percent of the profits go to Blocktec, LLC. |  | I8I | 2022-09-15
35) Each of the profit-takers will have a different address. We can plug those in on our own at the completion of the project. |  | I8I | 2022-09-15
36) Implement Functionality for Reviews. |  | I8I/Blocktec | 2022-09-15
37) Conduct 7-Step Cyber-security Penetration Testing & Walkthrough |  | I8I | 2022-09-15
38) Test on TestNet |  | I8I/Blocktec | 2022-09-15
39) Test on Ethereum Blockchain |  | I8I | 2022-09-15
40) Go Live.
Blocktec ENS Handle: blocktec.eth